## Action Tracker
Ref No | Action | Description | Owner | Dept | Priority | Source | Raised Date | Due Date | Status | % Complete | Comments | Evidence Required
LEG-001 | Rotate shared service account passwords | Quarterly rotation of shared service credentials. | Ahmed Al Balushi | IT Security | High | Internal Audit | 2026-08-11 | 2026-09-08 | In Progress | 70 | Rotation script tested, production rollout pending change approval. | Yes
LEG-002 | Review supplier contracts for data protection clauses | Legal review of top 10 supplier contracts. | Fatma Al Siyabi | Finance | Medium | Compliance Review | 2026-07-27 | 2026-09-30 | Not Started | 0 |  | Yes
LEG-003 | Patch legacy file server OS | Apply outstanding security patches to file server FS-02. | Yousuf Al Harthy | Operations | Critical | Vulnerability Scan | 2026-08-21 | 2026-09-05 | In Progress | 50 | Maintenance window booked for next weekend. | Yes
LEG-004 | Update incident response runbook | Incorporate lessons learned from March tabletop exercise. | Ahmed Al Balushi | IT Security | Low | Tabletop Exercise | 2026-08-31 | 2026-10-20 | Not Started | 0 |  | No
LEG-005 | Archive terminated employee accounts | Disable and archive accounts for leavers in Q2. | Fatma Al Siyabi | Finance | Medium | HR Audit | 2026-08-26 | 2026-09-20 | In Progress | 30 | Half of the list processed so far. | Yes